## HFWE
Screens | Front End Components | Hours | Back End Services | Hours2 | Comments | Sprint | hours
ScreenMockup of all the UI pages | View Page
Edit Page
New Page
User Interface Project Setup |  | 20
User Interface Roles Setup |  | 16
Role Based Navigation(Navigation Components Setup) |  | 20
User Interface Global Components Setup |  | 20
[5 empty] | Sprint 39 (C6,C7,C8,C9,) | Sprint 39 4/01 | 76
Dashboard | View Home Page Message | 8 | GetDashboardMessageService | 6 | Sprint 40 (C11,C12,E11,C16,E16,E17,E18,C19,(C21-4),C61) | Sprint 40 4/15 | 80
| Unit Testing | 4 |  |  | Sprint 41 ((C21-16),C22,C24,C26,E23,E24,E25,(C28-3)) | Sprint 41 4/29 | 80
[5 empty] | Sprint 42 ((C28-5),C29,C31,C32,(C34-2),E30,E31,E32,E33) | Sprint 42 5/13 | 74
[5 empty] | Sprint 43 (C34-2,C36,C37,C38,C39,C40,E36,E37,E38-1,) | Sprint 43 5/27 | 70 | 52
[5 empty] | Sprint 44 (E38-5,E39,E40,C41,C43,C44,C45,E43,E44,E45,C46,C49-6) | Sprint 44 6/10 | 72 | 72
Voting Settings | View Voting Setting Page | 10 | GetVotingSettingService | 8 | Sprint 45 (C49-4,C50,E49,E50,C51,C52,C58-7) | Sprint 45 6/24 | 80 | 80
|  |  | PostVotingSettingService | 8 | Sprint 46(C58-3,C62,C63) | Sprint 46 7/08 | 71 | 72
|  |  | PatchVotingSettingService | 8 |  | Sprint 47 7/22 |  | 27
| Unit Testing | 4
CandidateNominee-Central Office | Candidate Nominee Entry Search Form | 20
| Search Result for Employee Lists Grid | 20
|  |  | PostCandidateNomineeCOService | 10
| View Current Candidates Central Office Grid | 15 | GetCandidateNomineeCOService | 10
|  |  | DeleteCandidateNomineeCOService | 12
| Unit Testing | 4
CandidateNominee-Campus | Candidate Nominee Entry Search Form | 8
| Search Result for Employee Lists | 20
|  |  | PostCandidateNomineeCampusService | 8
| View Current Candidates Class Teacher Grid | 15 | GetCandidateNomineeCTService | 10
| View Current Candidates Campus Based Professional Grid | 10 | GetCandidateNomineeCBPService | 6
|  |  | DeleteCandidateNomineeService | 3---3
| Unit Testing | 4
Cast Vote- Campus | View Cast Vote Page Classroom Candidates Grid | 14 | GetCandidateNomineeCTService | 6
| Cast Vote Classroom TeacherCandidates | 15 | PostCandidateVoteCTService | 10
| View Cast Vote Page Campus Based Professional Grid | 4--6 | GetCandidateNomineeCBPService | 6
| Cast Vote Campus Based Professioanl Candidates | 10 | PostCandidateVoteCBPService | 6
| User Message after completing vote | 8 | GetCandidateVoteStatusService | 3---7
| Unit Testing | 4
Cast Vote- Central Office | View Cast Vote Page Central Office Nominee Grid | 15 | GetCandidateNomineeCOService | 6
| Cast Vote Central Office Candidates | 10 | PostCandidateVoteCOService | 6
| User Message after completing vote | 8 | GetCandidateVoteStatusService | 6
| Unit Testing | 4
Reports
Candidate Vote Results | Candidate Vote Result Page | 10 | GetSchoolYearService | 5
| View Candidate Vote Results Grid | 25 | GetCandidateVoteResultService | 25
| Export Report to excel | 10
| Unit Testing | 6
WebApi Configuration for Service Development |  | 10
MVC Controller development for Service Operations
Set up Database Connection from Service Application |  | 8
Develop Controller for consuming DB Enitities |  | 24
Integration of Access Security |  | 32 |  | Jibin 8
Total |  | 431 |  | 162
| Total | 593
Total |  |  |  | 22