## HFWE
Screens | Front End Components | Hours | Back End Services | Hours2 | Comments | Sprint | hours
ScreenMockup of all the UI pages | View Page | 20 |  |  | Done Sprint 37 | Sprint 37 3/04 | 80
| Edit Page |  |  |  |  | Sprint 38 3/18 | 40
| New Page |  |  |  |  | Sprint 39 4/01 | 72
[6 empty] | Sprint 40 4/15 | 80
User Interface Project Setup |  | 20 |  |  | Done Sprint 37. Roles considered are Administrator, SSO, Principal, School Coordinator, Teacher | Sprint 41 4/29 | 80
User Interface Roles Setup |  | 16 |  |  | Sprint 37 -> 38 | Sprint 42 5/13 | 80
Role Based Navigation(Navigation Components Setup) |  | 20 |  |  | Sprint 37 -> 38 | Sprint 43 5/27 | 80
User Interface Global Components Setup |  | 20 |  |  | Sprint 37 -> 38 | Sprint 44 6/10 | 72
[6 empty] | Sprint 45 6/24 | 80
Words List | View Words List Page | 8 | GetListOfWordsService | 6 | Sprint 38 (c7, c8, c9, c11, c12, c13) | Sprint 46 7/08 | 72
| Edit Words List Page | 12 | PostListOfWordsService | 6 | Sprint 39 ( e11, e12, e13, c16,c17,c18,e16,e17,e18, e19, c21) | Sprint 47 7/22 | 80 |  | 830 | 166 | 996
| New Words List Page | 6 | DeleteListOfWordsService | 4 |  | Sprint 48 8/05 | 80
|  |  | PatchListOfWordsService | 6 | Sprint 40 (c22, c23, e21, e22, e23, c26, c27, c28) | Sprint 49 8/19 | 80 | 976 | Dev Done
[5 empty] | Sprint 41 (e26, e27, e28, c30, c31, c32, e30, e31) | Sprint 50 9/02 | 80
Word List Details | View WordList Details Page | 6 | GetWordListDetailsService | 6 |  | Sprint 51 9/16 | 72
| Edit WordList Details Page | 10 | PostWordListDetailsService | 6 | Sprint 42 (c34, c37, c38,c39, e34, e37, e38, e39) | Sprint 52 9/30 | 80
| Add NewWord To WordList Page | 6 | DeleteWordListDetailsService | 4 |  | Sprint 53 10/14 | 80 | 1288
|  |  | PatchWordListDetailsService | 6 | Sprint 43 (c40, c43, c44, c45, e43, e44, e46) | Sprint 54 10/28 | 80
[5 empty] | Sprint 44 (e45, c49, e49, e50) | Sprint 55 11/11 | 80
Administration Window | View Administration Window Page | 10 | GetAdministrationWindowService | 8 | Sprint 45 (c50, c51, c53, e51) | Sprint 56 11/25 | 40
| Edit Administration Window Page | 12 | PostAdministrationWindowService | 8 | Sprint 46 (c52, c55, c56)
| New Administration Window Page | 8 | PatchAdministrationWindowService | 8 | Sprint 47( c56, c64, c65, c66)
Teachers List | View Teachers List Page | 10 | GetTeachersListService | 10
| Create Teachers Grid | 8 | GetListOfDistrictService | 10
| Create Teachers Results Evalution | 14 | GetListOfCampusService | 10
Teacher Details | View Teacher Details Page | 12 | GetTeacherService | 10
| Create Teacher Grid(for Students) | 10 | GetStudentsListService | 10
| Sort by Role | 8
Students List | View Students List Page | 20 | GetStudentsListService | 10
Student Details | View Student Details Page | 12 | GetStudentDetailsService | 10
| Create Student Grid | 8 | GetMissedWordsService | 10
| View Student Results Summary | 10 | GetAdministrationResultsService | 10
| View Missed Words List Page | 10
Test Screen
| Add Test Screen | 15 | GetTestScreenService | 10
| Edit Test Screen | 20 | PatchTestScreenService | 10
| View Test Screen | 10 | PostTestScreenService | 12 | Incase of Delete any Test Results for any Student
|  |  | DeleteTestScreenService | 5
Reports
Admin Report(District) | View School Results of selected District Report | 35 | GetSchoolResultsService | 15
Principal Report (Campus) | View School Results of assigned Campus Report | 30 | GetStudentSummaryService | 10
Coordinator Report (Multiple Campuses) | View School Results of selected Campus Report | 25 | GetMissedWordsService | 10
Teacher Report | View Teacher Report | 20
| View Missed Words % Report | 15
Unlock Test Functionality | Unlock Functionality for Admin, Principal, SC, Teacher | 20
Unit Testing |  | 30
WebApi Configuration for Service Development |  | 10
MVC Controller development for Service Operations
Set up Database Connection from Service Application |  | 8
Develop Controller for consuming DB Enitities |  | 24
Integration of Access Security |  | 32
Total |  | 590 |  | 230
| Total | 820