## Bugs Estimate
Task | Description | Priority | Estimate | Comments | Status
Able to add Mentee multiple times to Mentors |  | High | 15 |  | Open
CIC email notification | Need to verify that once a CIC is selected if they receive an email. | High | 8 |  | Open
MAS qa site throws error and has to be refreshed 2-3 times to work |  | High | 12 | Need Chris help in getting error Log from SharePoint | Open
Selecting an IP standard in Activity Log creation, kicks out from the session |  | High | 8 |  | Open
System must send Reminder Emails for incomplete logs per month | The requirement “The system should send reminder emails to Mentor if the required number of logs are not entered. The Admin should have the feature to set the number of days remaining to send the email.” | High | 40 | Need input from Chris on the best approach for implementation. Once the approach is defined will give a detailed estimate | Open
Unable to select a Mentee while adding an Activity Log |  | High | 8 |  | Open
Mentor role is missing from MAS |  | High | 16 |  | Open
Ability to update the IP/PE standards by the admin |  | Medium | 10 | Need more details from Vishal | Open
History needs to be maintained for the past 5 years |  | Medium | 40 |  | Open
Mentor must be able to edit only the current month activity logs |  | Medium | 10 |  | Open
Reminder emails to Mentor | The system should send reminder emails to Mentor if the required number of logs are not entered. The Admin should have the feature to set the number of days remaining to send the email.” Has not been developed yet. It will be a complicated solution and need time. | Medium | 32 |  | Closed
Add CIC and CIC email column to the Mentor Completion report. |  | Low | 12 |  | Open
In the Principal Dashboard, change Total Activity by MENTORS to MENTEES |  | Low |  | Vishal | Closed
Remove Mentor Name from the “Add Activity Log” link for the Mentor |  | Low | 4 |  | Open
Campus dropdown is not greyed out for principal role |  | Low | 5 |  | Open
Login page must be blank. |  | Low |  | Do we need to fix this | Closed
Campus Contacts do not get updated/refreshed immediately |  | Low | 8 |  | Open

## Missing Code Estimate
Task | Estimate | Comments
Top 3 campuses with most relationships | 25
Relationship status | 20
Relationship pending for approval | 10
Mentors without agreement accepted | 10
Total activities my Mentees | 15

## EDW Direct Call
Controller Name | Needed | Controller Method | Front End Component | Hours | Backend Components | Hours | EDW Tables | Description
CampusContactsController | Yes | GetAllCampusContacts | Populating CICDetailArray with all the information | 16 | Web service call to MAS | 8 | Staffs, StaffElectronicEmails, EducationOrganizations, JobCodes, StaffJobCode, JobFamilies | CIC ID in local DB and other details in EDW DB
| Yes |  |  |  | Web service call to Common to get CIC details | 12
| Yes | GetCampusContactsByCampusID | Populating CICDetailArray with all the information | 12 | Web service call to MAS CIC | 4 | Staffs,ElectronicEmails,EducationOrganizations,JobCodes,StaffJobCode,JobFamilies | CIC ID in local DB and other details in EDW DB
| Yes |  |  |  | Web service call to Common to get CIC details | 4
| No | GetCampusContactsByEmployeeID | Populating CICDetailArray with all the information | 10 | Web service call to MAS | 4 | Staffs,ElectronicEmails,EducationOrganizations,JobCodes,StaffJobCode,JobFamilies | CIC ID in local DB and other details in EDW DB
| No |  |  |  | Web service call to Common to get CIC details | 8
MenteeEndDatesController | No | GetAllMenteeEndDates | Populating MendeeEndDateArray with all the information | 20 | Web service call to MAS for MendeeEndDates | 8 | Staffs,ElectronicEmails,EducationOrganizations,JobCodes,JobFunctions,JobFamilies,EmployeeStatusTypes,EmployeeHISDStatusTypes,StaffQualificationAssociations,QualificationTypes,QualificationGroupAssociations,SalaryPlanTypes
| No |  |  |  | Web service call to Common to get MendeeEndDates details | 15
| No | GetMenteeEndDatesByCampusID | Populating MendeeEndDateArray with all the information | 12 | Web service call to MAS for MendeeEndDates | 4
| No |  |  |  | Web service call to Common to get MendeeEndDates details | 4
| No | GetMenteeEndDateByEmployeeID | Populating MendeeEndDateArray with all the information | 12 | Web service call to MAS for MendeeEndDates | 4
| No |  |  |  | Web service call to Common to get MendeeEndDates details | 4
CommonInfoController | No | GetUserInfoByLoginID | Populating userInfor data | 16 | Web service call to Common to get user data | 16 | Staffs,EducationOriganizations
MenteeInfoController | No | GetMentees | Populating Mentee Data | 20 | Web service call to Common to get Mentee Data data | 20 | Staffs,ElectronicEmails,EducationOrganizations,StaffAccomplishments,AccomplishmentTypes,JobCodes,JobFamilies,JobFunctions,EmployeeStatusTypes,EmployeeHISDStatusTypes,StaffQualificationAssociations,QualificationTypes,QualificationGroupAssociations,SalaryPlanTypes
| Yes | GetMenteesByCampusID | Populating Mentee Data | 14 | Web service call to Common to get Mentee Data data | 4
| No | GetMenteeInfoByEmployeeID | Populating Mentee Data | 10 | Web service call to Common to get Mentee Data data | 4
MentorMenteeRelationshipsController | Yes | GetAllMentorMenteeRelationships | Populating grid with mentor mentee principal CIC | 20 | WebService call to MAS for MentorMeteeRelation ship | 4
| Yes |  |  |  | Web service call to Common to get Mentee | 4
| Yes |  |  |  | Web service call to Common to get Mentor | 4
| Yes |  |  |  | Web service call to Common to get Principal | 4
ActivityLogsController | Yes | GetMentorsInActiveRelationshipByCampusID | Populate Data | 16 | Get Metor Deails from MAS | 4
| Yes |  |  |  | Get Mentor Details from Common | 10
| Yes | GetMenteesInActiveRelationshipByCampusID | Populate Data | 16 | Get Metor Deails from MAS | 4 | 4
| Yes |  |  |  | Get Mentor Details from Common | 6
| Yes | GetMenteesInActiveRelationshipByMentorID | Populate Data | 6 | Get Metor Deails from MAS | 2
| Yes |  |  |  | Get Mentor Details from Common | 2
| Yes | GetActivityLogsByCampusID | Populate Data | 10 | Get Activity log from MAS | 16
| Yes |  |  |  | Get User Data from Common | 8
| Yes | GetAllActivityLogs | Populate Data | 10 | Get Activity log from MAS | 4
| Yes |  |  |  | Get User Data from Common | 4
| Yes | GetActivityLogsByMenteeID | Populate Data | 10 | Get Activity log from MAS | 4
| Yes |  |  |  | Get User Data from Common | 4
| No | GetActivityLogsTotalTime | Populate Data | 8 | Get Activity log from MAS | 4
| No |  |  |  | Get User Data from Common | 4
| No | GetActivityLogsCompletedByMentor | Populate Data | 8 | Get Activity log from MAS | 4
| No |  |  |  | Get User Data from Common | 4