## Bugs Estimate
Task | Description | Priority | Estimate | Comments | Status | Owner | Box
Able to add Mentee multiple times to Mentors |  | High | 15 |  | Done | Praveen | Praveen
CIC email notification | Need to verify that once a CIC is selected if they receive an email. | High | 8 |  | Done | Jibin
MAS qa site throws error and has to be refreshed 2-3 times to work |  | High | 12 | Need Chris help in getting error Log from SharePoint | Open | Jibin
Selecting an IP standard in Activity Log creation, kicks out from the session |  | High | 8 |  | Open | Praveen | Praveen
System must send Reminder Emails for incomplete logs per month | The requirement “The system should send reminder emails to Mentor if the required number of logs are not entered. The Admin should have the feature to set the number of days remaining to send the email.” | High | 40 | Need input from Chris on the best approach for implementation. Once the approach is defined will give a detailed estimate | Open | Jibin
Unable to select a Mentee while adding an Activity Log |  | High | 8 |  | Open | Praveen | Praveen
Mentor role is missing from MAS |  | High | 16 |  | Done | Jibin
Ability to update the IP/PE standards by the admin |  | Medium | 10 | Need more details from Vishal | Open | Praveen
History needs to be maintained for the past 5 years |  | Medium | 40 |  | Open | Chris
Mentor must be able to edit only the current month activity logs |  | Medium | 10 |  | Open | Jibin
Add CIC and CIC email column to the Mentor Completion report. |  | Low | 12 |  | Open | Praveen | Jibin
Remove Mentor Name from the “Add Activity Log” link for the Mentor |  | Low | 4 |  | Done | Jibin
Campus dropdown is not greyed out for principal role |  | Low | 5 |  | Open | Praveen | Jibin
Campus Contacts do not get updated/refreshed immediately |  | Low | 8 |  | Open | Praveen | Jibin

## Missing Code Estimate
Task | Estimate | Owner
Top 3 campuses with most relationships | 25 | Jibin
Relationship status | 20 | Praveen
Relationship pending for approval | 10 | Jibin
Mentors without agreement accepted | 10 | Praveen
Total activities my Mentees | 15 | Jibin/Praveen

## EDW Direct Call
Controller Name | Needed | Controller Method | Front End Component | Hours | Backend Components | Hours | Owner | EDW Tables | Description
CampusContactsController | Yes | GetAllCampusContacts | Populating CICDetailArray with all the information | 16 | Web service call to MAS | 8 | Jibin | Staffs, StaffElectronicEmails, EducationOrganizations, JobCodes, StaffJobCode, JobFamilies | CIC ID in local DB and other details in EDW DB
| Yes |  |  |  | Web service call to Common to get CIC details | 12 | Jibin
| Yes | GetCampusContactsByCampusID | Populating CICDetailArray with all the information | 12 | Web service call to MAS CIC | 4 | Praveen | Staffs,ElectronicEmails,EducationOrganizations,JobCodes,StaffJobCode,JobFamilies | CIC ID in local DB and other details in EDW DB
| Yes |  |  |  | Web service call to Common to get CIC details | 4 | Praveen
MenteeInfoController | Yes | GetMenteesByCampusID | Populating Mentee Data | 14 | Web service call to Common to get Mentee Data data | 4 | Jibin
MentorMenteeRelationshipsController | Yes | GetAllMentorMenteeRelationships | Populating grid with mentor mentee principal CIC | 20 | WebService call to MAS for MentorMeteeRelation ship | 10 | Jibin
| Yes |  |  |  | Web service call to Common to get Mentee | 8 | Jibin
| Yes |  |  |  | Web service call to Common to get Mentor | 6 | Jibin
| Yes |  |  |  | Web service call to Common to get Principal | 6 | Jibin
ActivityLogsController | Yes | GetMentorsInActiveRelationshipByCampusID | Populate Data | 16 | Get Metor Deails from MAS | 4 | Praveen
| Yes |  |  |  | Get Mentor Details from Common | 10 | Praveen
| Yes | GetMenteesInActiveRelationshipByCampusID | Populate Data | 16 | Get Metor Deails from MAS | 4 | Praveen | 4
| Yes |  |  |  | Get Mentor Details from Common | 6 | Praveen
| Yes | GetMenteesInActiveRelationshipByMentorID | Populate Data | 6 | Get Metor Deails from MAS | 2 | Praveen
| Yes |  |  |  | Get Mentor Details from Common | 2 | Praveen
| Yes | GetActivityLogsByCampusID | Populate Data | 10 | Get Activity log from MAS | 16 | Jibin
| Yes |  |  |  | Get User Data from Common | 8 | Jibin
| Yes | GetAllActivityLogs | Populate Data | 10 | Get Activity log from MAS | 4 | Praveen
| Yes |  |  |  | Get User Data from Common | 4 | Praveen
| Yes | GetActivityLogsByMenteeID | Populate Data | 10 | Get Activity log from MAS | 4 | Jibin
| Yes |  |  |  | Get User Data from Common | 4 | Jibin